**PORTFOLIO DASHBOARD PROJECT STATUS GUIDELINES**

|  |  |  |  |
| --- | --- | --- | --- |
| **Constraint** | (On-Track) | (Some issues may impact project, but team is currently confident they can resolve) | (Experiencing issues outside the ability or control of the team to resolve without assistance) |
| **Health** | * If at least 2 constraints are green and none are red | * If at least 2 constraints are yellow and none are red | * If 2 or more constraints are red; if one constraint is red and one or more are yellow |
| **Scope** | * If no requests for scope change have been approved that cause a schedule or budget change more than 10% above baseline | * If 1 to 5 requests for change have been approved and cause the schedule or budget to move above 10% to 25% of baseline | * If 5 or more requests for change have been approved and cause the schedule or budget to move above 25% of baseline |
| **Schedule** | * If schedule is on track or the variance to baseline has not slipped more than 10% | * If schedule variance to baseline has slipped between 10% and 25% | * If schedule variance to baseline has slipped above 25% |
| **Budget** | * If budget is 50K over or 10% over baseline | * If budget is 50K-100K over or 10 - 25% over baseline | * If budget is 100K over or 25% over baseline |